## Template
START |  | 2021-05-10 |  | Target Publishing Date
Average PAGES per DAY |  |  |  | 2021-09-23
AUTHOR ENGAGEMENTS |  | YES/NO | SPECIFICS
VACATION PLANS |  | NO
CONFERENCES/SEMINARS |  | NO
WORK-RELATED PROJECTS/TRAVELS |  | NO
PERSONAL COMMITMENTS |  | NO
SCHEDULE GENERATED
Ch. No. | Title | Pages | Days | First Draft Delivery | Final DraftDelivery
1 | Introduction | 2 | 5 | 2021-05-15 | 2021-06-03
2 | Python and the Command Line | 18 | 7 | 2021-05-22 | 2021-06-10
3 | Intro to SQL | 12 | 7 | 2021-05-29 | 2021-06-17
4 | Visualizing Data | 16 | 7 | 2021-06-05 | 2021-06-27
5 | Introduction to Machine Learning | 10 | 7 | 2021-06-12 | 2021-07-11
6 | Unsupervised Machine Learning | 25 | 10 | 2021-06-22 | 2021-07-21
7 | Supervised Machine Learning | 40 | 14 | 2021-07-06 | 2021-08-04
8 | Natural Language Processing | 31 | 10 | 2021-07-16 | 2021-08-11
9 | Deep Learning in Biotech | 15 | 14 | 2021-07-30 | 2021-08-18
10 | End-to-End Model Development | 17 | 7 | 2021-08-06 | 2021-08-25
11 | Deploying with Flask | 12 | 7 | 2021-08-13 | 2021-08-30
12 | Deploying to the Cloud | 15 | 7 | 2021-08-20 | 2021-09-03
VITAL STATISTICS
CHAPTERS
FINAL FIRST DRAFT
WRITING TIME (DAYS)
WRITING TIME (WEEKS)
PUBLISHING DATE AS PER SCHEDULE
Formulas:
First Draft Delivery = IF([AUTHOR ENGAGEMENTS]<>"",D4+[SPECIFICS],"")
First Draft Delivery = IF([AUTHOR ENGAGEMENTS]<>"",[First Draft Delivery, row above]+[SPECIFICS],"")
Final DraftDelivery = IF([Title]<>"",F19+5,"")
Project Schedule

## with TR schedule
START |  | 2021-05-10 |  | Target Publishing Date
Average PAGES per DAY |  |  |  | 2021-09-23
AUTHOR ENGAGEMENTS |  | YES/NO | SPECIFICS
VACATION PLANS |  | NO
CONFERENCES/SEMINARS |  | NO
WORK-RELATED PROJECTS/TRAVELS |  | NO
PERSONAL COMMITMENTS |  | NO
SCHEDULE GENERATED
Ch. No. | Title | Pages | Days | First Draft Delivery | TR Delivery | Final DraftDelivery
1 | Introduction | 2 | 5 | 2021-05-15 | 2021-05-29 | 2021-06-03
2 | Python and the Command Line | 18 | 7 | 2021-05-22 | 2021-06-05 | 2021-06-10
3 | Intro to SQL | 12 | 7 | 2021-05-29 | 2021-06-12 | 2021-06-17
4 | Visualizing Data | 16 | 7 | 2021-06-05 | 2021-06-19 | 2021-06-27
5 | Introduction to Machine Learning | 10 | 7 | 2021-06-12 | 2021-06-29 | 2021-07-11
6 | Unsupervised Machine Learning | 25 | 10 | 2021-06-22 | 2021-07-13 | 2021-07-21
7 | Supervised Machine Learning | 40 | 14 | 2021-07-06 | 2021-07-23 | 2021-08-04
8 | Natural Language Processing | 31 | 10 | 2021-07-16 | 2021-08-06 | 2021-08-11
9 | Deep Learning in Biotech | 15 | 14 | 2021-07-30 | 2021-08-13 | 2021-08-18
10 | End-to-End Model Development | 17 | 7 | 2021-08-06 | 2021-08-20 | 2021-08-25
11 | Deploying with Flask | 12 | 7 | 2021-08-13 | 2021-08-27 | 2021-08-30
12 | Deploying to the Cloud | 15 | 7 | 2021-08-20 | 2021-08-31 | 2021-09-03
VITAL STATISTICS
CHAPTERS
FINAL FIRST DRAFT
WRITING TIME (DAYS)
WRITING TIME (WEEKS)
PUBLISHING DATE AS PER SCHEDULE
Formulas:
First Draft Delivery = IF([AUTHOR ENGAGEMENTS]<>"",D4+[SPECIFICS],"")
First Draft Delivery = IF([AUTHOR ENGAGEMENTS]<>"",[First Draft Delivery, row above]+[SPECIFICS],"")
TR Delivery = IF([AUTHOR ENGAGEMENTS]<>"",[First Draft Delivery, row below]+7,"")
TR Delivery = IF([AUTHOR ENGAGEMENTS]<>"",[TR Delivery, row above]+4,"")
Final DraftDelivery = IF([Title]<>"",F19+5,"")
Final DraftDelivery = IF([Title]<>"",[TR Delivery]+3,"")
Project Schedule

## Pub schedule
START |  | 2021-05-10 |  | Target Publishing Date
Average PAGES per DAY |  |  |  | 2021-09-23
AUTHOR ENGAGEMENTS |  | YES/NO | SPECIFICS
VACATION PLANS |  | NO
CONFERENCES/SEMINARS |  | NO
WORK-RELATED PROJECTS/TRAVELS |  | NO
PERSONAL COMMITMENTS |  | NO
SCHEDULE GENERATED
Ch. No. | Title | Pages | Days | First Draft Delivery | TR Delivery | Final DraftDelivery | Publication Ready
1 | Introduction | 2 | 5 | 2021-05-15 | 2021-05-29 | 2021-06-03 | 2021-06-13
2 | Python and the Command Line | 18 | 7 | 2021-05-22 | 2021-06-05 | 2021-06-10 | 2021-06-20
3 | Intro to SQL | 12 | 7 | 2021-05-29 | 2021-06-12 | 2021-06-17 | 2021-06-27
4 | Visualizing Data | 16 | 7 | 2021-06-05 | 2021-06-19 | 2021-06-27 | 2021-07-07
5 | Introduction to Machine Learning | 10 | 7 | 2021-06-12 | 2021-06-29 | 2021-07-11 | 2021-07-21
6 | Unsupervised Machine Learning | 25 | 10 | 2021-06-22 | 2021-07-13 | 2021-07-21 | 2021-07-31
7 | Supervised Machine Learning | 40 | 14 | 2021-07-06 | 2021-07-23 | 2021-08-04 | 2021-08-14
8 | Natural Language Processing | 31 | 10 | 2021-07-16 | 2021-08-06 | 2021-08-11 | 2021-08-21
9 | Deep Learning in Biotech | 15 | 14 | 2021-07-30 | 2021-08-13 | 2021-08-18 | 2021-08-28
10 | End-to-End Model Development | 17 | 7 | 2021-08-06 | 2021-08-20 | 2021-08-25 | 2021-09-04
11 | Deploying with Flask | 12 | 7 | 2021-08-13 | 2021-08-27 | 2021-08-30 | 2021-09-09
12 | Deploying to the Cloud | 15 | 7 | 2021-08-20 | 2021-08-31 | 2021-09-03 | 2021-09-13
VITAL STATISTICS
CHAPTERS
FINAL FIRST DRAFT
WRITING TIME (DAYS)
WRITING TIME (WEEKS)
PUBLISHING DATE AS PER SCHEDULE
Formulas:
First Draft Delivery = IF([AUTHOR ENGAGEMENTS]<>"",D4+[SPECIFICS],"")
First Draft Delivery = IF([AUTHOR ENGAGEMENTS]<>"",[First Draft Delivery, row above]+[SPECIFICS],"")
TR Delivery = IF([AUTHOR ENGAGEMENTS]<>"",[First Draft Delivery, row below]+7,"")
TR Delivery = IF([AUTHOR ENGAGEMENTS]<>"",[TR Delivery, row above]+4,"")
Final DraftDelivery = IF([Title]<>"",F19+5,"")
Final DraftDelivery = IF([Title]<>"",[TR Delivery]+3,"")
Publication Ready = IF([YES/NO]<>"",[Final DraftDelivery]+10,"")
Project Schedule